## Pre-Production Summary
Project Name
Total Estimated Assets & Implementation Times | (See other sheets for breakdowns)
Total Model Time: | 0
Total Rigging and Animation Time: | 5.8
Total Scripting Time: | 25.1
Total VFX Time: | 22.4
Total SFX Time: | 26.6
Total UI Time: | 21.7
Total Time: | 101.6
Scale
Unit Size:
Notes:
Unknowns

## Models
Models | Category | Model Time | UV Map Time | Texture Time | LightingTime | Approval/Adjustment Time | Total Time For Model
Low-Res Models
Motor 1 | Large | 5 minutes |  |  |  |  | 0
Motor 2 | Large | 4 minutes
Motor 3 | Large | 5 minutes
Motor 4 |  | 3 minutes
Arm 1 |  | 4 minutes
Arm 2 |  | 2 minutes
Arm 3 |  | 2 minutes
Arm 4 |  | 2 minutes
Drone Body |  | 30 minutes
Blade 1 |  | 4 minutes
Blade 2 |  | 1 minute
Blade 3 |  | 1 minute
Blade 4
Large
Total Low-Res Model Time:
Medium-Res Models
Back_Motor | Medium | 7 hours 40 minutes
Front_Motor | Medium | 35 minutes
Foot | Medium | 30 minutes
Hinge | Medium | 20 minutes
Body | Medium | 3 hours 55 minutes
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Total Medium-Res Model Time:
High-Res Models
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Small
Total High-Res Model Time:
Total Model Time:

## Rigging and Animation
Model To Animate | Category | Rig Time | Animation Time | Implement Time | Test Time | Approval/Adjustment Time | Total Time For Animation
Characters
BabaYagaHut | Large | 3 | 1 | 0.5 | 0.3 | 1 | 5.8
[6 empty] | Total Character Animation Time: | 5.8
[6 empty] | Total Rig & Animation Time: | 5.8

## Scripts
Scripts | Category | Coding Time | Implement Time | Test Time | Approval/Adjustment Time | Total Time For Script
Player
PlayerMovement | Medium | 2 | 0.5 | 0.5 | 1 | 4
CameraControl | Small | 1 | 0.3 | 0.2 | 1 | 2.5
Jump | Small | 1 | 0.3 | 0.2 | 2 | 3.5
[5 empty] | Total Player Script Time: | 10
Game Events
GameReset | Small | 1 | 0.3 | 0.2 | 0.5 | 2
PlayerDeath | Small | 1 | 0.2 | 0.1 | 0.5 | 1.8
CollectItem | Medium | 2 | 0.5 | 0.5 | 1 | 4
[5 empty] | Total Events Script Time: | 7.8
Rendering
CullingObjects | Small | 1 | 0.2 | 0.2 | 1 | 2.4
TexReplacer(?) | Medium | 2 | 0.4 | 0.5 | 2 | 4.9
[5 empty] | Total Rendering Script Time: | 7.3
[5 empty] | Total Script Time: | 25.1

## VFX
VFX | Category | Art/Script Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For VFX
Camera
Shake | Medium | 0.3 | 1.5 | 0.3 | 1 | 3.1
Collect | Small | 0.3 | 1 | 0.2 | 1 | 2.5
Death | Medium | 0.3 | 1 | 0.3 | 1 | 2.6
[5 empty] | Total Camera VFX Time: | 8.2
Environmental
Fog | Large | 2 | 2 | 0.4 | 1 | 5.4
[5 empty] | Total Environmental VFX Time: | 5.4
Event
WoodCrack | Small | 1 | 1 | 0.5 | 0.5 | 3
DustPoof | Small | 1 | 1 | 0.5 | 0.5 | 3
CollectSparkle | Small | 1 | 1 | 0.3 | 0.5 | 2.8
[5 empty] | Total Event VFX Time: | 8.8
[5 empty] | Total VFX Time: | 22.4

## SFX
SFX | Category | Recording/Editing Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For SFX
Player
Damage | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Jump | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Landing | Small | 0.3 | 1 | 0.2 | 0.5 | 2
HeavyLanding | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Death | Medium | 1 | 1 | 0.2 | 1 | 3.2
[5 empty] | Total Player SFX Time: | 11.2
Environmental
BackgroundCreaks | Large | 2 | 1 | 0.5 | 1 | 4.5
BabaYagaHutStomp | Medium | 0.5 | 2 | 0.5 | 1 | 4
[5 empty] | Total Environmental SFX Time: | 8.5
Event
WoodCrack | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
DustPoof | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
CollectSparkle | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
[5 empty] | Total Event SFX Time: | 6.9
[5 empty] | Total SFX Time: | 26.6

## UI
UI | Category | Art/Scripting Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For UI
Camera
CrackScreen | Medium | 2 | 2 | 0.2 | 0.5 | 4.7
Collectable | Small | 1 | 1 | 0.2 | 0.5 | 2.7
FadeScreen | Small | 0.3 | 2 | 0.2 | 1 | 3.5
[5 empty] | Total Camera UI Time: | 10.9
Front End
TitleScreen | Large | 2 | 1 | 0.5 | 1 | 4.5
[5 empty] | Total Front End UI Time: | 4.5
Pause
PauseMenu | Large | 3 | 2 | 0.3 | 1 | 6.3
[5 empty] | Total Pause UI Time: | 6.3
[5 empty] | Total UI Time: | 21.7